Paper-free transport roadmap

This roadmap translates the 2025 paper-free transport project into practical steps for designated operators (DOs), airlines, ground handling agents (GHAs) and customs/security authorities.
It complements existing UPU guidance and tools on the paper-free transport page and is intended to support planning and implementation during 2026.

Concept and benefits

Paper-free transport replaces CN38/41/47 paper documents in the air transport leg with standardized electronic data (CARDIT, RESDIT, PRECON, RESCON, ITMATT), while keeping appropriate exceptions for security and customs where required. ​

The main benefits reported by operators include better visibility and tracking, fewer operational errors, reduced paper handling at airports, and environmental and cost savings: Paper-free flyer

Step-by-step implementation on selected routes

Step 1 – Select candidate routes and partners

- Choose 1–3 priority routes where volumes justify effort and partners show interest (initial focus on Asia, then Arab, Latin America & Caribbean, Africa, Europe).

- Identify key partners per route (origin/destination DOs, airlines, GHAs, customs/security where relevant) and nominate a paper-free focal point for operations and IT/EDI in each DO.

- Step 2 – Check preconditions and data readiness

- Verify that required messages (CARDIT, RESDIT, PRECON, RESCON, ITMATT) can be generated and exchanged; use IPS configuration guidance and EDI manuals where applicable. ​

- Use existing monitoring tools (e.g. CAPE paper-free transport reports, EDI performance indicators, IQRS, EMS SMART) to check message timeliness, completeness and linking quality on the selected routes. ​

Step 3 – Agree operational procedures and fallback

- Using the “Paper-free route implementation guidelines for Posts and carriers”, agree route-specific procedures with partners (handover points, who sends what message when, how electronic evidence replaces CN38). ​

- Define clear fallback procedures (e.g., temporary printing, use of DocPORT to retrieve CN documents) for rare cases where electronic data is unavailable or rejected by security/customs. ​

Step 4 – Pilot and progressively remove paper

- Run a time-bound pilot (e.g. 3–6 months) on the route, maintaining a minimal CN38 presence at the beginning if required by local rules or partners. Guideline for implementing paper-free transport​

- Based on performance reports and partner feedback, reduce and then eliminate CN38 copies for that route, maintaining only any legally required exceptions.

Process flow for ​DOs not yet implementing paper‑free

For designated operators that have not yet started any paper-free route, the following basic sequence is recommended:

- Check the UPU transport / paper-free page. Review the concept, benefits and list of available tools on the UPU transport – paper-free transport page.​

- Watch the paper-free implementation videos. Use the paper-free transport module videos as an introduction for management, operations and IT/EDI teams.​

- Read the paper-free transport implementation guidelines. Study the “Paper-free route implementation guidelines for Posts and carriers” to understand preconditions, checklists and the pilot route process.​

- Access the paper-free transport workspace. Log into the workspace, consult the contact database and identify potential partner DOs and airlines that are already paper-free-capable.​​

- Evaluate current performance and data readiness. Analyze EDI quality and operational performance on candidate routes using IQRS, QCS, SMART, CAPE and other available monitoring tools, where applicable.​​

- Contact partners and prepare activation in the PF agreement tool
Discuss candidate routes with partner DOs, airlines and GHAs; then formalize and activate the route using the paper-free transport agreement tool, contacting the UPU for access or support if needed.​​

Using existing UPU tools and resources

4.1 Guidance and documentation

- Paper-free transport page – Central entry point with concept, key documents, tools and links. UPU transport page - paper-free transport​

- Paper-free route implementation guidelines – Pre-conditions, step-by-step process, checklists and tripartite agreement templates for DOs and carriers - Guideline for implementing paper-free transport​

4.2 Technical configuration and systems

- Implementation of the paper-free transport module (videos/docs) – Explains how to map operational processes to EDI messages and configure systems.

- Paper free video 1 - Introduction

- Paper-free transport video 2: Operations and messaging procedures

- Paper-free video 3: Process to make a paper-free route

- Paper-free transport in IPS guide – Provides IPS-specific instructions for enabling paper-free routes and stopping automatic printing - Paper free transport in IPS​

4.3 Operational tools and workspaces

- Paper-free transport workspace & contact database – Lists paper-free-capable DOs/carriers and facilitates bilateral/trilateral coordination - Paper-free transport workspace_PF contact database  ​

- CAPE paper-free reports, agreement tool, DocPORT – Support route selection, agreement management and retrieval of CN documents when needed (request contact via zoran.stevanovic@upu.int or transport@upu.int)

Addressing main concerns from the survey

| What operators reported in the survey | How to address it with existing tools |
| --- | --- |
| Airport security, customs, airlines and GHAs still require CN38 | - Use the implementation guidelines and Postal Transport Guide security sections as references in discussions; - Share UPU flyer and examples; set up trilateral meetings using the contact database and workspace. UPU transport page - paper-free transport​ - Request an access to DocPORT to support printing copies of CN38 in case if it is required for GHA, security, customs. |
| Lack of EDI exchange or poor data quality | - Activate EDI exchange with your partners and work on the improvement of CARDIT/RESDIT/PRECON/RESCON/ITMATT; use CAPE/IPC/IQRS data to identify gaps and target corrective actions on candidate routes: - IQRS - transport dashboard - https://www.emssmart.post/ - https://qcsmail.ptc.post/ ​ - https://cape.ipc |
| Internal procedures still require printed CN documents | Use guideline checklists to review and update internal SOPs; run short internal training sessions using the videos and flyer to support change: see section 4.2 and use Guideline for implementing paper-free transport​ |
| Limited awareness of existing tools and materials | Direct all teams to the paper-free transport page and workspace as the “one-stop shop” for guidelines, tools, contacts and recordings. UPU transport page - paper-free transport​ |
| Need for more training and capacity building | Use the video module and existing documents for self-training, complementing with upcoming 2026 webinars and regional workshops announced via email and the UPU site / see section 4.2 of this document​ |

Support plan and call to action

The International Bureau will support postal operation in implementation through:

- A series of global and regional webinars with live demonstrations of paper-free processes and tools (including data evaluation with IT tools)​

- Updated practical guidance (short notes, templates and examples) focused on security/customs acceptance, airline/GHA collaboration and internal procedure changes

Designated operators are invited to:

- Nominate a national paper-free focal point (operations + IT/EDI)

- Identify and communicate 1–3 candidate routes for pilot or extension of paper-free transport in 2026.

This roadmap can be used as a checklist during your internal evaluation and in discussions with partner DOs, airlines, GHAs and authorities to plan concrete steps towards paper-free transport.

____________